## Sheet1
TASKSHEET
Team members: |  |  | Project information
Name |  | Student ID | Project title | Build a hotel service managament system
Huynh Lu Anh Khoa |  | 18520916 | Course code | SE104.L23.PMCL
Ha Thuc Dang Khoa |  | 18520914 | Planned by | Ha Thuc Dang Khoa
Le Van Tri
No. | Task title | Date of preparation |  | Taker | Status
|  | Planned start date | Planned completed date
System modelling
1 | Entity relation diagram | 2021-01-06 | 15/06/2021 | Ha Thuc Dang khoa | Finish
2 | Sequence diagram | 2021-01-06 | 15/06/2021 | Le Van Tri | Finish
3 | System requirement specification | 2021-01-06 | 15/06/2021 | Ha Thuc Dang khoa | Finish
4 | System design specification | 2021-01-06 | 15/06/2021 | Ha Thuc Dang khoa | Finish
5 | State diagram | 2021-01-06 | 15/06/2021 | Huynh Lu Anh Khoa | Finish
6 | Use case specification | 2021-01-06 | 15/06/2021 | Ha Thuc Dang khoa | Finish
7 | Use case diagram | 2021-01-06 | 15/06/2021 | Ha Thuc Dang khoa | Finish
8 | Activity diagram | 2021-01-06 | 15/06/2021 | Le Van Tri | Finish
9 | Requirement analysis | 2021-01-06 | 15/06/2021 | Whole team | Finish
10 | Class diagram | 2021-01-06 | 15/06/2021 | Ha Thuc Dang khoa | Finish
Implementaion
11 | Record service usage | 15/06/2021 | 30/06/2021 | Huynh Lu Anh Khoa | Finish
12 | Booking
13 | Checking out
14 | Payment
15 | Invoicing
Testing
16 | Record service usage | 15/06/2021 | 30/06/2021 | Huynh Lu Anh Khoa | Finish
17 | Booking
18 | Checking out
19 | Payment
20 | Invoicing
21 | Sample database | 15/06/2021 | 15/06/2021 | Le Van Tri | Finish